## Sheet0
PROJECT TIMELINE
Project: Smart Parking System |  | Duration: 2 weeks
Task | Assigned to | Start Date | End Date
Hardware & Maquette design | Nermeen Noaman | 2025-08-16 | 2025-08-28
WEB App development | Manar Samir | 2025-08-16 | 2025-08-28
ESP32 Code / Hive MQ | Menna Mohammed | 2025-08-16 | 2025-08-22
Subabase & Its connection with Hive MQ via NODE-RED | Sondos Yasser | 2025-08-16 | 2025-08-22
Flask API | Sohair Mohammed | 2025-08-22 | 2025-08-28
AI / ML Logic | Wafaa Galal | 2025-08-22 | 2025-08-28